ITT 837 – Staffordshire & Stoke GP OOHs

Section 1.9.17

Please detail how you will prepare for any Contract Exit in the event an alternative Provider winning a future ITT for the services or variants of the services.

The Bidder has provided a comprehensive and appropriate response to the question - Pass.
The Bidder has failed to provide a comprehensive and appropriate response to the question – Fail

As a national provider we are experienced in mobilising and demobilising contracts to ensure a smooth transition with no or minimal patient impact.

Vocare plan contract exits or demobilisations in the same manner as a mobilisation. Our demobilisation plans will be developed collectively with the CCG to ensure the requirements are captured and fully understood. These requirements are then enacted by a demobilisation team organised into six workstreams. A demobilisation Director would be appointed and will chair weekly meetings to review progress against the key milestones and plan. We follow Prince 2 LITE project management principles.

Where possible the demobilisation team will not be delivering the transitioning service due to;

The requirements to continue to deliver the current service until the transfer date and any potential conflict or TUPE related challenges. This approach provides an independent transfer that achieves all milestones transparently.

Our demobilisation plan includes expected resources, timeframes, milestones, deliverables for all elements of the service.

Our demobilisation manager will capture activity, using the plan to monitor progress by/across workstreams and against milestones. Workstream Leads will develop mitigations to minimise delay/impact, checking everyone understands activities/progress.

We expect weekly demobilisation-progress meetings between the CCG, new provider and our mobilisation leads using the demobilisation plan and summaries submitted pre-meeting for CCG review with top risks from the demobilisation risk register. We will extend invitations to the CCG representatives to attend workstream/demobilisation meetings.

Issues will be escalated through governance meetings between the providers and the CCGs with senior representatives from both organisations (e.g. our demobilisation Director). We will agree defined escalation routes within the CCG for reporting demobilisation-related issues outside scheduled meetings.

All demobilisations to date have been undertaken successfully and delivered to requirements and timeframes.

﻿